## Sheet1
Group Number: | 13
Group Members: | Szymon Chirowski (242621), Hristiyan Georgiev (241236), Mohammadali Jaberi (244437), Aristotelis Protopapas (234062)
Mentor: | Elavendan Rajendran
Date | Type of Meeting (Standup / Retro) | Attendees | Link to Recording | Summary of Meeting
2025-05-23 | Retro | Szymon Chirowski, Hristian Georgiev, Elavendan Rajendran | None - Mentor was attending | Discussing the details of the project, creating the time plan
2025-05-26 | Standup | Szymon Chirowski, Hristian Georgiev, Mohammadali Jaberi, Aristotelis Protopapas | https://edubuas-my.sharepoint.com/:v:/g/personal/242621_buas_nl/EamOdo8-bpFDlVWaOTR-8DcBdDsNA-8dY1rJLTXogU3syg?e=DIX2Ik&nav=eyJyZWZlcnJhbEluZm8iOnsicmVmZXJyYWxBcHAiOiJTdHJlYW1XZWJBcHAiLCJyZWZlcnJhbFZpZXciOiJTaGFyZURpYWxvZy1MaW5rIiwicmVmZXJyYWxBcHBQbGF0Zm9ybSI6IldlYiIsInJlZmVycmFsTW9kZSI6InZpZXcifX0%3D | Discussing the group proposal details, Szymon was presenting the contribution rules to the team's repo, onboarding people who were absent on last retro with project details
2025-05-27 | Retro | Szymon Chirowski, Hristian Georgiev, Mohammadali Jaberi, Aristotelis Protopapas, Elavendan Rajendran | Call with Chirowski, Szymon (242621)-20250527_095804-Meeting Recording.mp4 | In the 27-05-2025 meeting, Team 13 clarified the project's focus on event prediction, reviewed EDA progress, and established a project timeline. They also addressed data quality issues, agreed on using a Markdown format for documentation, and assigned tasks and responsibilities to be tracked via Trello.
2025-05-28 | Standup | Szymon Chirowski, Hristian Georgiev, Mohammadali Jaberi, Aristotelis Protopapas | Call with Georgiev, and 2 others-20250528_165920-Meeting Recording.mp4 | In the meeting on 28-05-2025, Team 13 reviewed the current state of the dataset and confirmed readiness to begin initial model development using Apple stock data. Tasks for the upcoming week were delegated, including modeling, data validation, and finalizing the UI/UX documentation.
2025-06-02 | Standup | Szymon Chirowski, Hristian Georgiev, Mohammadali Jaberi, Aristotelis Protopapas | Call with Georgiev, and 2 others-20250602_130114-Meeting Recording.mp4 | In the 02-06-2025 meeting, Team 13 addressed major concerns with Aristotelis’ lack of contribution, as he again failed to deliver or explain his assigned UI/UX task. The team agreed to report the issue to the mentor and possibly reassign the task. Meanwhile, Hristiyan presented structured feature engineering work, Mohammadali and Szymon shared modeling progress, and the team discussed fallback plans for data coverage. Task assignments for Week 5 were finalized and deadlines set.
2025-06-04 | Standup | Szymon Chirowski, Hristian Georgiev, Mohammadali Jaberi, Aristotelis Protopapas | Call with Georgiev, and 2 others-20250604_133101-Meeting Recording.mp4 | In the 04-06-2025 meeting, Team 13 reviewed Szymon's EDA and finalized modeling responsibilities, assigning specific models to each member. Aristotelis presented a working dashboard, which will be simplified and refined based on team feedback. The team also discussed data resampling strategy and planned next-day tasks, including model performance evaluation and integration preparation.
2025-06-05 | Standup | Szymon Chirowski, Hristian Georgiev, Mohammadali Jaberi, Aristotelis Protopapas | Meeting in THIS IS GROUP CHAT!!!-20250605_130201-Meeting Recording.mp4 | In the meeting on 05-06-2025, Team 13 reviewed progress on model development, with members sharing updates on their respective tasks. Mohammadali achieved 30% accuracy using a weighted technique, while Szymon resolved environment issues and tested baseline models (ZeroR: 51%, Persistent: 6%). Hristiyan worked on a combined CNN+GRU model but faced performance and speed challenges. Aristotelis committed to starting a CNN classification model and collaborating with Mohammadali. The team also discussed logistical concerns due to an upcoming train strike and finalized action items, including model adjustments, environment fixes, and preparation for the retrospective meeting.
2025-06-06 | Retro | Szymon Chirowski, Hristian Georgiev, Mohammadali Jaberi, Aristotelis Protopapas, Elavendan Rajendran | Call with Protopapas, and 1 other-20250606_100938-Meeting Recording.mp4 | In the meeting, the team reviewed progress on various modeling tasks, including LSTM, hybrid CNN-GRU, and RF/DT models, agreeing to prioritize performance optimization. The CNN model and dashboard development were flagged as behind schedule, with Aristotelis receiving a formal warning to align work with project goals or risk losing contribution credit. Clarifications on SQL tasks and documentation were also addressed, with no blockers reported.
2025-06-10 | Standup | Szymon Chirowski, Hristian Georgiev, Mohammadali Jaberi, Aristotelis Protopapas, Elavendan Rajendran | Call with Protopapas, Aristotelis (234062)-20250610_101516-Meeting Recording.mp4 | In the 10/06/2025 meeting, Team 13 reviewed critical issues with Aristotelis’ CNN model and his inability to explain or validate the implementation, leading to a complete loss of trust in his contributions. The mentor officially declared him unreliable, set his group contribution score to 0, and authorized the team to continue the project without involving him further. The UI task was reassigned, and remaining work was distributed among the active team members.
2025-06-11 | Standup | Szymon Chirowski, Hristian Georgiev, Mohammadali Jaberi | Meeting in THIS IS GROUP CHAT!!!-20250611_200311-Meeting Recording.mp4 | In the 11/06/25 meeting, Team 13 finalized their approach to UI deployment, ML pipeline structure, and project modularization. Hristiyan committed to completing the Flask-based dashboard by Friday, while Szymon outlined a clear separation of code modules. The team agreed to stop model development and focus on hyperparameter tuning, logging, and formatting to align with MLOps standards.
2025-06-12 | Standup | Szymon Chirowski, Hristian Georgiev, Mohammadali Jaberi | Meeting in THIS IS GROUP CHAT!!!-20250612_130028-Meeting Recording.mp4 | In the 12/06/25 meeting, Team 13 reviewed their recent progress, including UI implementation, initial LSTM tuning, and poetry setup. They planned next-day tasks focused on finalizing backend integration, completing tuning, and updating Trello. The main blocker—UI merge—was addressed, enabling backend progress to continue as scheduled.
2025-06-16 | Standup | Szymon Chirowski, Hristian Georgiev, Mohammadali Jaberi | Meeting in THIS IS GROUP CHAT!!!-20250616_125954-Meeting Recording.mp4 | In the 16/06/25 meeting, Team 13 assigned all remaining tasks for the final sprint, aiming to complete everything by Thursday midday. The team discussed the README structure, MLOps deliverables like unit tests and deployment, and reviewed blockers such as hyperparameter tuning, which requires clarification from their teacher. Responsibilities were distributed clearly among members, ensuring accountability for the final project submission.
2025-06-17 | Retro | Szymon Chirowski, Hristian Georgiev, Mohammadali Jaberi | Call with Hayden, Avril-20250617_131817-Meeting Recording.mp4 | In the 17/06/25 meeting, Team 13 aligned on finalizing outstanding project components, with a particular focus on MLOps deliverables, documentation, and the final project template. Tasks were reviewed for progress, including UI deployment, unit testing, and presentation preparation. The team also clarified that Aristotelis remains excluded from task planning and delivery due to prior mentor approval.
2025-06-18 | Standup | Szymon Chirowski, Hristian Georgiev, Mohammadali Jaberi | Meeting in THIS IS GROUP CHAT!!!-20250618_130015-Meeting Recording.mp4 | In the 18/06/25 meeting, Team 13 conducted a focused session via Teams to finalize their project preparations. The team reviewed the draft of the final presentation, offering constructive feedback to improve clarity, professionalism, and visual appeal—such as summarizing text-heavy slides, removing raw code, and revising the EDA heatmap. They planned a clear structure for the EU AI Act compliance slide and agreed on a “Questions?” closing slide. Each member updated the group on their task progress, confirming timelines to complete all outstanding work by the next day. The team addressed the challenge of an unresponsive member by deciding to reassign the UI/UX presentation part to Hristiyan and to notify their mentor about the issue. Action points included revising the presentation, finalizing documentation, adding back-testing, and submitting peer feedback. The next meeting was scheduled for 19/06/25 to continue final preparations.
2025-06-19 | Standup | Szymon Chirowski, Hristian Georgiev, Mohammadali Jaberi | Meeting in THIS IS GROUP CHAT!!!-20250619_130300-Meeting Recording.mp4 | In the 19/06/25 meeting, Team 13 finalized their contribution points and confirmed fair task distribution. Each member updated the group on their remaining work, all on track for timely completion. Presentation roles were assigned clearly, with Mohammadali, Hristiyan, and Szymon covering specific slides in project order. The team agreed to proceed without the absent member, Aristotelis, and will inform teachers if he appears unprepared. Action items focus on finishing documentation, testing, and presentation prep before the block ends.